## Release Overview
LifeReady Training — COMP229 Part 2 Agile Tracker
Owner: Amir Saad (301473849) ¦ Project: First Aid, CPR/AED & BLS Training Website ¦ Release: Part A — Frontend/Backend Integration and CRUD
Release status | Value
Completed Part A tasks | 5
In progress tasks | 2
Planned Part B tasks | 3
Production security audit | 0 high-severity production vulnerabilities
Video requirement | Professor waiver recorded — no Part 2 video
Part A completion notes
The React frontend is connected to the Express/MongoDB API. Users can sign up, sign in, manage their profile, and sign out. Administrators manage training classes and locations through protected CRUD pages. The remaining Part A handoff work is to capture current screenshots, commit and push the release, and submit the updated tracker with the GitHub link.

## Product Backlog
Product Backlog — LifeReady Training
ID | User story | Priority | Acceptance criteria | Status | Release area
P2-01 | As a visitor, I can see a branded landing page and upcoming first-aid classes. | High | The logo, site name, and scheduled courses load from the API. | Done | Part A
P2-02 | As a visitor, I can create an account and sign in securely. | High | Sign-up/sign-in forms validate input and create a session. | Done | Part A
P2-03 | As a signed-in user, I can access My Profile and sign out. | High | The menu shows My Profile and Sign out; profile can be updated or deleted. | Done | Part A
P2-04 | As an administrator, I can create, read, update, and delete training classes. | High | Protected class-management page performs full CRUD through the API. | Done | Part A
P2-05 | As an administrator, I can create, read, update, and delete locations. | High | Protected location-management page performs full CRUD through the API. | Done | Part A
P2-06 | As a learner, I can filter classes by category, location, and date. | Medium | Course catalogue updates visible class cards using the selected filters. | Done | Part A
P2-07 | As an administrator, I can view users and contact messages. | Medium | Protected user directory and message inbox load data from the API. | Done | Part A
P2-08 | As a student developer, I can submit an understandable GitHub release. | High | README is current and a Part A commit is pushed to GitHub. | In Progress | Part A handoff
P2-09 | As a student developer, I can show active Agile tracking. | High | This product backlog and task board are included with the submission. | Done | Part A handoff
P2-10 | As a tester, I can run Cypress AI end-to-end tests. | High | Core user and admin flows have repeatable E2E test evidence. | Planned | Part B
P2-11 | As a developer, I can evaluate performance with Lighthouse. | Medium | Lighthouse report identifies and documents optimisation actions. | Planned | Part B
P2-12 | As a deployer, I can host the completed project on Render. | Medium | Production environment variables and deployed health check are verified. | Planned | Final deployment

## Task Board
Task Board — LifeReady Training
Task ID | Task | Owner | Status | Release area | Evidence / next action
T-01 | Build public home page and course catalogue integration | Amir Saad | Done | Part A | Home page displays API course data
T-02 | Implement sign-up, sign-in, sign-out, and protected profile | Amir Saad | Done | Part A | Cookie session and profile CRUD
T-03 | Implement administrator training-class CRUD screens | Amir Saad | Done | Part A | Create, edit, list, and delete classes
T-04 | Implement administrator location CRUD screens | Amir Saad | Done | Part A | Locations control public filters
T-05 | Add responsive navigation, current-page state, and My Profile link | Amir Saad | Done | Part A | NavLink active state and authenticated actions
T-06 | Update README and Part 2 Agile documentation | Amir Saad | Done | Part A | Repository is understandable for marking
T-07 | Commit and push the Part A release to GitHub | Amir Saad | In Progress | Part A handoff | Perform after final visual check
T-08 | Capture current UI and CRUD screenshots for submission evidence | Amir Saad | In Progress | Part A handoff | Use browser and admin pages
T-09 | Create Cypress AI end-to-end test suite and evidence | Amir Saad | Planned | Part B | Do after Part A is submitted
T-10 | Run Lighthouse and document performance optimisation | Amir Saad | Planned | Part B | Do after functional testing
T-11 | Prepare Render deployment settings and production smoke test | Amir Saad | Planned | Final deployment | Do after tests and performance review